## Sheet1
ADAMAWA STATE BUREAU OF PUBLIC PROCUREMENT
PROCUREMENT PLAN FOR WORKS
Procuring Entity (Name of the Organization)
| Financial Year (Budget Appropriation) |  |  |  |  | 2026
| BASIC DATA | [7 empty] | BIDDING PERIOD |  |  |  | CONTRACT FINALIZATION AND IMPLEMENTATION
| S/N | Description of contract | Bill of Quantity/ BEME | Procurement Method | Estimated Amount | Pre or Post Qualification | Prior or Post Review | In-House Plan Vs Actual | Preparation & Submission of Bid document | Bid Invitation Date | Bid Closing & Opening Date | Submission of Bid Evaluation Report | Budgetary Provision | Approving Authority | Date Of Contract Award | In-House Plan Vs Actual | Final Cost | Expected date of Completion
| 1. | ELECTRIFICATION OF BENGHUM IN FUFORE LGA (GDP FUFORE) | BOQ | SELECTIVE |  | NILL | NILL | NILL |  | 2026-10-08 | 17/8/2026 | 19/08/2026 | 250000000 | MDA | 20/08/2026 | NILL
| 2. | REHABILATION OF ELETRICITY SUPPLY INFRASTRUC TURE FROM OPALO TO HOKKI IN LAMURDE LGA | BOQ | SELECTIVE |  | NILL | NILL | NILL |  | 2026-10-08 | 17/8/2026 | 19/8/2026 | 98100000 | MDA | 20/8/2026 | NILL
| 3. | PROVISION FOR SOLAR SREET LIGHT BANJIRAM,IN GUYUK LGA (GDP GUYUK) | B.O.Q | SELECTIVE |  | NILL | NILL | NILL |  | 2026-10-08 | 17/8/2026 | 19/8/2026 | 50000000 | MDA | 20/8/2026 | NILL
| 4. | RURAL ELETRIFICATION OFMBEMUN IN LAMURDE LGA (GDP LAMURDE) | BOQ | SELECTIVE |  | NILL | NILL | NILL |  | 2026-10-08 | 17/8/2026 | 19/8/2026 | 283000000 | MDA | 20/8/2026 | NILL
| 5. | PROVISION OF SOLAR STREET LIGTH(7.5KM) AT YOLA NORTH (GDP YOLA NORTH) |  | SELECTIVE |  | NILL | NILL | NILL |  | 2026-10-08 | 17/8/2026 | 19/8/2026 | 500000000 | MDA | 20/8/2026 | NILL
6.