## Sheet1
ADAMAWA STATE BUREAU OF PUBLIC PROCUREMENT
PROCUREMENT PLAN FOR WORKS
Procuring Entity (Name of the Organization)
| Financial Year (Budget Appropriation) |  |  |  |  | 2026
| BASIC DATA | [7 empty] | BIDDING PERIOD |  |  |  | CONTRACT FINALIZATION AND IMPLEMENTATION
| S/N | Description of contract | Bill of Quantity/ BEME | Procurement Method | Estimated Amount | Pre or Post Qualification | Prior or Post Review | In-House Plan Vs Actual | Preparation & Submission of Bid document | Bid Invitation Date | Bid Closing & Opening Date | Submission of Bid Evaluation Report | Budgetary Provision | Approving Authority | Date Of Contract Award | In-House Plan Vs Actual | Final Cost | Expected date of Completion
| 1. | RENOVATION OF OFFICE WITHIN THE ADAMAWA STATE SECRETARIAT FOR ADSUPDA | BOQ | DIRECT LABOUR | 100000000 | Pre | Pre | - | 31/08/2026 | 2026-01-09 | 2026-07-09 | 2026-10-09 | 150000000 | Exco | 14/09/2026 | - | - | -
| 2. | RENOVATION OF ADAMAWA STATE CORRECTIONAL SERVICE CONTTROLLER | BOQ | DIRECT LABOUR | 12O,OOO,OOO | Pre | Pre | - | 31/08/2026 | 2026-01-09 | 2026-07-09 | 2026-10-09 | 100000000 | Exco | 14/09/2026 | - | - | -
3.
4.
5.
6.